## Description
JSON tools
Application for programmers who need to reformat or filter data structures saved in JSON format and to compare the structures with each other. JSON tools application allows you to both minify the unminified JSON representation, as well as the reverse operation (with any blanks and new lines added). The application will be available via GUI, as well as as a remote API, so it can be integrated with existing tools.
Note: we do not require creating your own parser for JSON representation, you can successfully use libraries - e.g. Jakson library (mapping objects to JsonNode type).

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As an external software developer, I can use the available functions remotely via REST to be able to integrate the tool with other applications. | 20 | 3 | 1 | o Input in JSON format containing the structure to be transformed o Input transformed to an object model o Output in JSON format o REST API allows you to run any currently implemented function.
As a developer, I can get a minified JSON structure from JSON full format to reduce data size. | 12 | 2 | 1 | o The shape of the data does not change o The result does not contain unnecessary spaces o The result fits to one line o Error reported for incorrect JSON
As a developer, I can get the full structure in JSON format from minified JSON format to improve the readability of the data. | 12 | 1 | 1 | o The shape of the data does not change o The result is properly indented o Error reported for incorrect JSON
As a developer, I can get a JSON-formatted structure with only certain keys to simplify the structure. | 10 | 1 | 1 | o The shape of the data does not change o All keys are removed from JSON objects except those passed on input o Error reported for incorrect JSON
As a developer, I can get a JSON structure without specific keys to simplify the structure. | 10 | 1 | 1 | o The shape of the data does not change o JSON objects have only selected keys (all others are removed) o Error reported for incorrect JSON
As a developer, I can compare two texts (e.g. representing the data structure in JSON formats) expecting the application to show lines where there is a difference. | 9 | 2 | 1 | o Correctly reported lines with differences o No differences are found if both texts are blank o If one text is blank, the whole other is marked as difference
As a user, I can utilise the application via the user interface |  | 10 |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: | Creating a functional API interface for JSON manipulation with documentation, CI and compilation setup.
Product Backlog Item | Tasks | Labour intensity
As an external software developer, I can use the available functions remotely via REST to be able to integrate the tool with other applications. |  | 3
| Server setup | 1.5
| Endpoints skeleton | 0.5
| Basic client | 1
As a developer, I can get a minified JSON structure from JSON full format to reduce data size. |  | 2
| Downloading libraries | 1
| As a developer, I can get a minified JSON structure from JSON full format to reduce data size. | 1
As a developer, I can get the full structure in JSON format from minified JSON format to improve the readability of the data. |  | 1
| As a developer, I can get the full structure in JSON format from minified JSON format to improve the readability of the data. | 1
As a developer, I can get a JSON-formatted structure with only certain keys to simplify the structure. |  | 1
| As a developer, I can get a JSON-formatted structure with only certain keys to simplify the structure. | 1
As a developer, I can get a JSON structure without specific keys to simplify the structure. |  | 1
| As a developer, I can get a JSON structure without specific keys to simplify the structure. | 1
As a developer, I can compare two texts (e.g. representing the data structure in JSON formats) expecting the application to show lines where there is a difference. |  | 2
| Comparing lines | 2
GitHub setup with tags |  | 1
Compilation setup with CI |  | 2
Creating documentation |  | 1
Transitioning from excel to GitHub projects |  | 1
Logging |  | 1
UML
| UML planning | 3
| Drawing UML | 1
Implementing decorator patterns |  | 1